## Sheet1
Student	Dody Suria Wijaya		Date	29/03/2006
Program			Program #	Homework 7
Instructor	Alexi		Language	Java

Summary	Plan	Actual	To Date
Minutes/LOC	2.1	1.39	1.01
LOC/Hour	28.57	43.04	59.53

Program Size	Plan	Actual	To Date			Prev To Date	Prev Actual
Total New&Changed	20	33	127			94	29
Max size	30
Min size	10

Time in Phase	Plan	Actual	To Date	To Date %		Prev To Date	Prev Actual
Planning	2	4	9	7.03		5	2
Design	16	5	22	17.19		17	16
Code	18	28	59	46.09		31	18
Compile	1	1	5	3.91		4	1
Test	4	7	29	22.66		22	4
Postmortem	1	1	4	3.13		3	1
Total	42	46	128	100		82
Max time	63
Min Time	21

Defects Inject		Actual	To Date	To Date %		Prev To Date
Planning		0	0	0		0
Design		0	1	11.11		1
Code		2	8	88.89		6
Compile		0	0	0		0
Test		0	0	0		0
Total		2	9	100		7
Defects Removed		Actual	To Date	To Date %		Prev To Date
Planning		0	0	0		0
Design		0	0	0		0
Code		0	0	0		0
Compile		0	3	50		3
Test		2	3	50		1
Total		2	6	100		4